## Slide 1: Controls Issues 3rd Injection test meeting 9th Sep 2008
Eugenia Hatziangeli
Input from I. Kozsar, J.C. Bau, M. Sobzak, JJ Gras, C. Roderick, M.Pace, N. Stapley, P. Charrue, G. Kruk, M. Misiowiek, A. Bland, M. Arruat, S. Page, P. Charrue, N. Hobian
E. Hatziangeli

## Slide 2: Timing
Standing issues:
  with the mismatch between the tables loaded in the master LHC MTG and the ones in the Operational application
  and CRT LTIM (disabled & wrong payload)
  RF synch problem
All issues have been resolved. New versions of the LHC gateway RT task, LTIM and CBCM have been deployed last week and used without any problems during the 3rd Injection test
E. Hatziangeli 3rd test meeting report 9th Sep. 2008

## Slide 3: CMW/FESA Servers
Several bugs on CMW (RDA) and FESA were corrected prior to 3rd Injection test
  Formal RDA release 2.6.6
XTIM server stable
Collimators servers stable
BT servers are stable
BI servers stability is improving. Remaining issues
  BCTFRLHC – work around is found – move to short arrays and RDA2.6.6 has eliminate the problem
    Will come back to boolean arrays to locate cause and fix it after 10th
  BLMs - issue with notification between fesa server and client- work around is implemented in FESA which will inhibit the issue to appear
    Proper fix after 10th
PO instabilities – Rare GW crash after an application is closed when CMW has not finished its work
  Fix is prepared but will not be deployed unless needed– in agreement with S. Page
E. Hatziangeli 3rd test meeting report 9th Sep. 2008

## Slide 4: Logging
General logging OK
LHC Collimators full logging OK
  XPOC-event triggered data logging testing OK
New Meas API deployed
  Parallelization
  Fixed rate logging and on change
  SDDS logging on disk when Meas DB not available
New API was deployed succesfully for
  BPM logging
  BLM logging
  FGCs – 0.5Hz fixed rate + on change
  No dataloss from the loggers due to the new API
Duplicate JMS service available – OPERATIONAL for CCC/CCR clients & PUBLIC for others
Issues encoutered
  Meas DB backup inhibited logging – has now stopped indefinitely
  Transfer of data from MeasDB to Logging DB took long time – reasons understood
  BLM logger was disconnected from JMS – reasons understood and corrected in BLM logger
E. Hatziangeli 3rd test meeting report 9th Sep. 2008

## Slide 5: RBAC
RBAC settings during the 3rd Injection test:
  RBAC-enable = true
  RBAC-policy = lenient
RBAC behaved correctly during the test
  No inappropriate denial of access to device was encountered
Equipment groups tested and ready
  BI OK
  PO OK
  BT OK
  Collimators not fully RBACed OK
  RF – no RBAC OK
RBACed OP LHC application
  50% completed
10th Sept
  Remain as on the 5th Sep. - change nothing
  In case of problems – clear and quick procedure to remove RBAC is provided and communicated to OP
  https://wikis.cern.ch/display/LAFS/RBAC+Panic+page
  RBAC-policy = lenient
    No token – grant
    Property without rules – grant
    Property with rules - check rules
E. Hatziangeli 3rd test meeting report 9th Sep. 2008

## Slide 6: Summary
Issues with the Timing are fixed and tested successfully
FESA/CMW servers stability improved – remaining issues are not blocker – fixes have been deployed
Logging – new API deployed for BLM, BPM, FGC ensured no loss of data
RBAC with lenient policy behaved as expected => no interference with the test
  RBAC remains with the lenient policy for the 10th Sep.
  Procedure to remove it, if needed, is communicated
E. Hatziangeli 3rd test meeting report 9th Sep. 2008