## Slide 1: LHC Injection Test
Reminder of LSS layouts with BI
Involved systems:
  BTV
    LSS2 and LSS3
  BPM
    Position and Intensity
  BLM
Date presently foreseen 9+10 August but could slip to the weekend after (DSO)

## Slide 2: LSS layouts 2L, 2R, 3L
BPMWI
BPMSX
BPMSW
BPMSX
BTVST
BTVM
BPMWB
BPMSW
BTVSI
BTVSI
????

## Slide 3: BTV (screens)
  TI2.BTVI.29506 (MSI entry)
  LHC.BTVSS.6L2.B1 (MSI exit)
  LHC.BTVSI.A5L2.B1 (MKI entry)
  LHC.BTVSI.C5L2.B1 (MKI exit)
  LHC.BTVST.A4L2.B1 (TDI entry)
    Bake-out finished last week
      Hardware installation finished this week
      A few hours needed to complete system commissioning
  LHC.BTVM.7L3.B1

## Slide 4: BPM system for beam#1
A total of 16 (TI2 + LSS2) +27 (2R) + 26 (3L) + 2 (LSS3) = 71 BPMs (+?)
BPM Name | Comment | Position
BPMIH.29304 | Last HOR BPMI in TI2 | 
BPMIV.29504 | Last VER BPMI in TI2 | 
 |  | Injection point
BPMYB.5L2 |  | Q5L2
BPMYB.4L2 |  | Q4L2
BPMWI.4L2 | Warm | 
 |  | TDI
BPMSX.4L2 | Warm | D1L2
BPMS.2L2 | Cold (rotated 45 degrees) | Q2L2
BPMSW.1L2 | Warm | Q1L2
 |  | IP2 (ALICE)
BPMSW.1R2 | Warm | Q1R2
BPMS.2R2 | Cold (rotated 45 degrees) | Q2R2
BPMSX.4R2 | Warm | D1R2
BPMWB.4R2 | Warm | 
BPMYB.4R2 |  | Q4R2
BPMR.5R2 |  | Q5R2
BPM.6R2 |  | Q6R1
BPM_A.7R2 |  | Q7R2
Arc 2-3 (Q8R2 -> Q8L3) | Continuous cryostat | 
BPM.7L3 |  | Q7L3
BPM.6L3 |  | Q6L3
BPMWE.5L3 | Warm | Q5L3 ??

## Slide 5: BPM (Position)
Installation and commissioning of tunnel electronics in LSS2 (L+R) required
BPM status:
  All BPMs now connected to cables
  Rest of the work will take place in UA23/27 and on the surface (SR2 and SR3)
A total of 6 front-end systems (LSA concentrator)
FIFO acquisition mode used, triggered using LHC injection events (no need for LHC BST)

## Slide 6: BPM intensity
Intensity
  A single (few) intensity module(s) can be installed anywhere in the LHC ring (we propose Q8 point 3L)
    Provides ~10% absolute accuracy with pilot bunches

## Slide 7: BLM LHC
We expect few (single) data bins with loss values (40usec) for a pilot bunch
  (maybe different around the collimator used as dump ?)
Acquisitions could be based on either of (or all ?):
  “Standard” running sum (1second integration at 1Hz, good choice)
    Already included in the logging, doesn’t need LHC BST
    Would show up as a ‘blip’ lasting 1second on a fixed-display
  “Capture” triggered with dedicated LHC timing event (a few msec before actual injection)
    Needs LHC BST for freezing hardware buffer
    40 micro-second sampling with depth = 2048 (82msec)
    Integrate all values to give single value per BPM (front-end or LSA) ??
  “Xpoc” buffer triggered with dedicated LHC timing event at the time of the injection
    Needs LHC BST for freezing hardware buffer
    40 micro-second sampling with depth = 200 (8 msec)
BLM LSA concentrator to be commissioned for Xpoc and “Capture”
  5 BLM front-end systems (2L, 2C, 2R, 3L, 3C) required
  State of application(s) and fixed-displays ?
A few hardware issues to be sorted (point 2 and 3)
Include connections to BIC with thresholds ?
Enough time for radioactive source test ?
List of BLMs on next slide, enough or add ‘mobile/extra’ ones?

## Slide 8: BLM monitors
LSS3 L (Q6):
LSS2 L+R
(+BLMI monitors on MSI and MKI)
 | LEFT |  |  |  | RIGHT | 
Position | #IC | #SEM |  | Position | #IC | #SEM
MSIB | 3 | 3 |  | BPMSW |  | 1
MSIA | 3 | 3 |  | MQXA | 10 | 
Q5 | 6 |  |  | MQXB | 8 | 
Q4 | 6 |  |  | MBX | 2 | 
MBRC | 2 |  |  | TCTVB | 1 | 1
TCTH | 1 | 1 |  | TCLIA | 1 | 1
TDI | 3 | 3 |  | TCTH | 1 | 1
TCTVB | 1 | 1 |  | MBRC | 2 | 
MBX | 2 |  |  | Q4 | 6 | 
MQXA | 10 |  |  | Q5 | 6 | 
MQXB | 8 |  |  | TCLIB | 1 | 1
BPMSW |  | 1 |  |  |  | 
 | LEFT | 
Position | #IC | #SEM
Q6 | 6 | 
TCLA (B2) | 1 | 1
TCP | 1 | 1
TCHSH | 1 | 
TCAPA | 1 | 1
Position | #IC | #SEM
MQ | 6 | 
MBA | 3 | 
MBB | 3 | 
ARC standard:

## Slide 9: What’s planned (so far)
Commission TI 2 end, injection and thread to IR3
Commission trajectory acquisition and correction
Polarity checks (BPMs and correctors)
Commission Beam Loss Monitor system
Optics measurements
Aperture checks
Effect of magnetic cycle
Field quality checks
(Quench limits and BLM response)
Setting up of injection machine protection
More discussions starting this afternoon

## Slide 10: What’s missing
BTV:
  Commissioning of BTVST
  Check video transmission from UJ33
BLM:
  Sort out remaining hardware issues
  Decide on the acquisition mode(s) used
BPM:
  Install missing hardware modules (WBTN+INT)
  Commission hardware
  Calibrate and store values in LSA database
  Commission software including LSA concentrator